## Color
PROJECT: Tesis
Contoso, Ltd. |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Hayden Cook
Project start date: | 2024-08-14 |  |  |  |  | August | [20 empty] | September | [27 empty] | October
Scrolling increment: | 0 | time axis 2024-08-14 to 2024-10-08
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2024-08-14 to 2024-10-08
2024-08-14
Data (Creacion) |  |  |  | 2024-08-15 | 51
Selecion de Poligonos | Low Risk | Juan | 0% | 2024-08-15 | 6
Extraccion Informacion | High Risk | Juan | 0% | 2024-08-21 | 14
Version Inicial para Primera estimacion | Milestone | Juan | 0% | 2024-09-04 | 1 | bar: 2024-09-04
Procesamiento TIFS | Med Risk | Juan | 0% | 2024-08-30 | 14
Asignacion de Poligonos a TIFS | High Risk | Juan | 0% | 2024-09-13 | 9
Homogenisacion de las fuentes | Low Risk | Juan | 0% | 2024-09-22 | 11
Datos version 2 | Goal | Juan | 0% | 2024-10-03 | 2 | 2024-10-03: 2; 2024-10-04: 2
Modelos |  |  |  | 2024-08-30 | 100
lectura U-Net | Low Risk | Juan | 0% | 2024-08-30 | 7
Implemntacion Datos genericos U-Net | Med Risk | Juan | 0% | 2024-09-06 | 7
Implementacion Datos Propios U-Net | High Risk | Juan | 0% | 2024-09-13 | 10
Presentacion Resultados U-Net | Goal | Juan | 0% | 2024-09-23 | 1 | 2024-09-23: 2
lectura Detectron2 (Meta AI) | On Track | Juan | 0% | 2024-09-24 | 7
Implemntacion Datos genericos Detectron2 (Meta AI) | Med Risk | Juan | 0% | 2024-10-01 | 7
Implementacion Datos Propios Detectron2 (Meta AI) | High Risk | Juan | 0% | 2024-10-08 | 10
Presentacion Resultados Detectron2 (Meta AI) | Goal | Juan | 0% | 2024-10-18 | 1
Lectura DeepLab (Google) | Low Risk | Juan | 0% | 2024-10-19 | 7
Implemntacion Datos genericos DeepLab (Google) | Med Risk | Juan | 0% | 2024-10-26 | 7
Implementacion Datos Propios DeepLab (Google) | High Risk | Juan | 0% | 2024-11-02 | 10
Presentacion Resultados DeepLab (Google) | Goal | Juan | 0% | 2024-11-12 | 1
Lectura YOLOv5 | Low Risk | Juan | 0% | 2024-11-13 | 7
Implemntacion Datos genericos YOLOv5 | Med Risk | Juan | 0% | 2024-11-20 | 7
Implementacion Datos Propios YOLOv5 | High Risk | Juan | 0% | 2024-11-27 | 10
Presentacion Resultados YOLOv5 | Goal | Juan | 0% | 2024-12-07 | 1
Lectura SegNet | Low Risk | Juan | 0% | 2024-11-13 | 7
Implemntacion Datos genericos SegNet | Med Risk | Juan | 0% | 2024-11-20 | 7
Implementacion Datos Propios SegNet | High Risk | Juan | 0% | 2024-11-27 | 10
Presentacion Resultados SegNet | Goal | Juan | 0% | 2024-12-07 | 1
Estimaciones (Econometricas) |  |  |  | 2024-08-14
Lectura metodologias | Med Risk | Juan | 0% | 2024-08-14 | 21
Elecion Metodologia 1 (CS) | Low Risk | Juan | 0% | 2024-09-04 | 10
Simulacion 1 | Low Risk | Juan | 0% | 2024-09-14 | 10
Prueba Supuestos | Med Risk | Juan | 0% | 2024-09-24 | 10
Implementacion real | High Risk | Juan | 0% | 2024-10-04 | 14
Metodologia 2 | On Track | Juan | 0% | 2024-10-18 | 10
Simulacion 2 | Med Risk | Juan | 0% | 2024-10-28 | 10
Prueba Supuestos | On Track | Juan | 0% | 2024-11-07 | 10
Implementacion real | High Risk | Juan | 0% | 2024-11-17 | 14
Revisar resultados | Low Risk | Juan | 0% | 2024-12-01 | 7
Docuemntos |  |  |  | 2024-08-14 | 71
Portada | Med Risk | Juan | 0% | 2024-08-14 | 7
Introducción | High Risk | Juan | 0% | 2024-08-21 | 14
Descripción detallada de los datos y/o del modelo teóric | High Risk | Juan | 0% | 2024-09-04 | 7
Metodología detallada | Med Risk | Juan | 0% | 2024-09-11 | 7
Resultados principales | Med Risk | Juan | 0% | 2024-09-18 | 14
Resultados secundarios | Med Risk | Juan | 0% | 2024-10-02 | 7
Ejercicios de robustez | Med Risk | Juan | 0% | 2024-10-09 | 7
Conclusiones | Med Risk | Juan | 0% | 2024-10-16 | 7
Referencias | Low Risk | Juan | 0% | 2024-10-23 | 1
Seminario |  |  |  | 2024-08-14
Entrega 1 | Goal | Juan | 0% | 2024-09-27 | 1 | 2024-09-27: 2
Entrrega 2 | Goal | Juan | 0% | 2024-11-29 | 1
Reuniones
Reunion Tesis 1 | Milestone | Juan | 0% | 2024-08-14 | 1 | bar: 2024-08-14
Reunion Tesis 2 | Milestone | Juan | 0% | 2024-09-18 | 1 | bar: 2024-09-18
Reunion Tesis 3 | Milestone | Juan | 0% | 2024-10-16 | 1
Reunion Tesis 4 | Milestone | Juan | 0% | 2024-11-20 | 1
Reunion Tesis Extra | Milestone | Juan | 0%
To add more data, Insert new rows ABOVE this one